## Tasks
Project Tracker Template
Track tasks, owners, dates and progress. Overdue tasks are flagged automatically.
Today
Task | Owner | Status | Priority | Start | Due | % complete | Days left | Flag
Kickoff meeting | Ana | Done | High | 2026-10-05 | 2026-10-07 | 100%
Requirements doc | Ben | Done | High | 2026-10-07 | 2026-10-14 | 100%
Design mockups | Cara | In progress | High | 2026-10-15 | 2026-11-03 | 60%
Build prototype | Ben | In progress | Medium | 2026-10-21 | 2026-11-14 | 30%
User testing | Ana | Not started | Medium | 2026-11-12 | 2026-11-22 | 0%
Launch plan | Cara | Not started | Low | 2026-11-16 | 2026-11-29 | 0%
Go live | Ben | Not started | High | 2026-12-02 | 2026-12-06 | 0%
Free template by Softotech Solutions (softotech.net). For educational and general use only, not financial or legal advice.

## Summary
Project Summary
Counts update from the Tasks sheet.
Measure | Value
Total tasks
Done
In progress
Not started
On hold
Overdue
Average % complete
Free template by Softotech Solutions (softotech.net). For educational and general use only, not financial or legal advice.

## Read me
Project Tracker Template
1. List tasks with owner, start and due dates and percent complete.
2. Choose status and priority from the drop-downs.
3. Days left and the flag (OVERDUE, Due soon, On track) update daily.
4. The Summary sheet counts tasks by status and averages progress.
5. Sample project included. Overwrite it.
Colour key: yellow cells = type your own numbers or text ¦ green cells = calculated automatically (do not overwrite)
Free template by Softotech Solutions (softotech.net). For educational and general use only, not financial or legal advice.